## Contract Mgmt & Admin (MA)
KFSU Portfolio Monitoring Tool — Contract Management & Administration (MA)
Government of Kiribati — Ministry of Finance and Economic Development — Kiribati Fiduciary Services Unit
• CONTRACT REF & DESCRIPTION: Must match exactly what was entered in the Procurement Plan (PP) tab. These fields auto-populate in the tool when the award date is set.
• CONTRACTOR: Full legal name of the contracting firm or individual as written in the signed contract.
• GRANT NO.: Primary grant funding this contract. For contracts co-financed by multiple grants (e.g. STSWP), enter the primary grant here and add others via the tool.
• CONTRACT VALUE (ORIG): Amount as written in the signed contract in the original currency (AUD or USD). USD CONTRACT VALUE: ADB — read from LFIS (no conversion). WB AUD — multiply by Client Connection rate at award date.
• DATE COLUMNS (blue, cols I–K): Enter as DD-Mon-YYYY (e.g. 12-Aug-2026). Click any blue date cell to see the entry guide. YYYY-MM-DD also accepted. Never use MM/DD/YYYY.
• CONTRACT STATUS: Select from dropdown — Active, Completed, Terminated, or Suspended. If Terminated or Suspended, enter reason in the last column.
• VARIATIONS: Record all contract amendments (time extensions, cost changes, scope changes) in the Variations sheet of this workbook.
• Copy data rows only — do NOT paste the header row into the tool.
📅 Blue = date columns (click for format guide) 🟡 Yellow = contract status dropdown 📋 Variations → use the Variations sheet
Contract ref (auto from PP) | Description (auto from PP) | Contractor | Payment class | Grant no. | Contract currency | Contract value (original currency) | USD contract value | Award date (e.g. 21/08/2026) auto from PP | Commencement date (e.g. 21/08/2026) | Actual completion date (e.g. 21/08/2026) | Contract status | Termination / Suspension reason (if applicable)
ATFP-CTR-001 | Design and supervision services | ABC Consulting Ltd | Consulting | IDA E5200 | USD | 125000 | 125000 | 2026-08-12 | 2026-09-01 |  | Active
ATFP-CTR-002 | Supply of laboratory equipment | XYZ Supplies Ltd | Goods | 0652-KIR | AUD | 83500 | 52605 | 2026-07-15 | 2026-08-01 | 2027-06-30 | Completed
ATFP-CTR-003 | National consultant — FM Officer | Jane Doe | Consulting | IDA E5200 | AUD | 45000 | 28350 | 2026-03-01 |  |  | Terminated | Contract terminated by mutual agreement — scope no longer required

## Variations
KFSU Portfolio Monitoring Tool — Contract Variations Register
Government of Kiribati — Ministry of Finance and Economic Development — Kiribati Fiduciary Services Unit
• CONTRACT REF: Must exactly match the contract ref in the MA sheet of this workbook and in the Contracts tab of the tool.
• VARIATION NO.: Sequential number for each variation per contract (e.g. 1, 2, 3). Each variation is a separate row.
• VARIATION TYPE: Select from dropdown — Time Extension, Cost Variation, Both (Time + Cost), or Other.
• REVISED END DATE: New contract end date after time extension. Leave blank if this is a cost-only variation.
• REVISED CONTRACT VALUE (USD): New total contract value in USD after cost variation. Leave blank if time extension only.
• DESCRIPTION: Brief description of the variation — scope change, key personnel, extension reason etc.
• APPROVAL REFERENCE: Donor NOL reference or internal approval number authorising the variation.
• DATES: DD-Mon-YYYY format (e.g. 12-Aug-2026). YYYY-MM-DD also accepted.
Contract ref | Variation no. | Variation type | Revised end date (e.g. 21/08/2026) | Revised contract value (USD) | Description / Reason | Approval reference | Approval date (e.g. 21/08/2026)
ATFP-CTR-001 | 1 | Time Extension | 2027-12-31 |  | Request from contractor due to COVID-19 travel restrictions — 6 month extension approved | NOL-2026-001 | 2026-09-15
ATFP-CTR-001 | 2 | Cost Variation |  | 135000 | Additional tasks added to scope — design of Phase 2 components | NOL-2026-008 | 2026-11-01
ATFP-CTR-002 | 1 | Both (Time + Cost) | 2027-09-30 | 92000 | Scope expanded to include additional testing equipment — time and cost adjusted | NOL-2026-012 | 2026-11-20

## USD Conversion Guide
USD Conversion Guide — Contract Management & Administration
Contract scenario | Contract value (original currency) | USD contract value — how to get it
WB grant, AUD contract (national consultant / local goods) | Enter AUD amount from contract | AUD × Client Connection rate at award date = USD. Source: select "Client Connection (WB)" in tool
WB grant, USD contract (international consultant) | Enter USD amount from contract | Same figure in both columns. Source: select "Client Connection (WB)" in tool
ADB grant, USD contract | Enter USD amount from contract | Read from LFIS. Same figure in both columns. Source: select "LFIS (ADB)" in tool
ADB grant, AUD contract (national consultant) | Enter AUD amount from contract | Read USD equivalent directly from LFIS — do NOT convert manually. Source: select "LFIS (ADB)" in tool
Multi-grant contract (e.g. STSWP) | Enter primary grant value here | Add other grants via tool. Total USD = sum of all grant allocations. Use the Grant allocation(s) button in MA tab.

## Valid values
Valid Values Reference — Contract Management & Administration
Payment class (col D)
Consulting | Column D
Non-consulting | Column D
Goods | Column D
Works | Column D
IOC | Column D
TW | Column D
Currency (col F)
AUD | Column F
USD | Column F
NZD | Column F
EUR | Column F
GBP | Column F
Contract status (col L)
Active | Column L
Completed | Column L
Terminated | Column L
Suspended | Column L
Variation type (Variations sheet col C)
Time Extension | Variations sheet
Cost Variation | Variations sheet
Both (Time + Cost) | Variations sheet
Other | Variations sheet