## Procurement Plan (PP)
KFSU Portfolio Monitoring Tool — Contracts: Procurement Plan (PP)
Government of Kiribati — Ministry of Finance and Economic Development — KFSU
• CONTRACT REF: Unique identifier (e.g. ATFP-CTR-001). Must match exactly when record moves to the MA tab.
• PLANNED BUDGET (USD): Overall budget envelope allocated for this activity.
• PLANNED AWARD DATE: Target award date from the procurement plan (YYYY-MM-DD).
• ACTUAL AWARD DATE: Date contract was signed. Entering this moves the record to the MA section automatically.
• CURRENCY (col F) / ACTUAL CONTRACT VALUE (cols F-H): Pick the currency the contract was actually signed in (col F: AUD/USD/NZD/EUR/GBP), enter the value in that currency (col G), then enter the USD equivalent (col H) if you already know it (e.g. from a prior conversion) - otherwise leave col H blank and the tool will calculate it from the KFSU-managed exchange rate for that currency and date. If Currency = USD, col H should simply match col G.
• PLANNED COMPLETION DATE: Expected end date from the procurement plan (YYYY-MM-DD).
• DATES (columns D, E, I — highlighted blue): Enter as DD-Mon-YYYY (e.g. 12-Aug-2026). Click any blue date cell to see the entry guide. YYYY-MM-DD also accepted. Never use MM/DD/YYYY — it is ambiguous between US and UK formats.
Contract ref | Description | Planned Budget (USD) | Planned Award Date (e.g. 21/08/2026) | Actual Award Date (e.g. 21/08/2026) | Currency | Actual Contract Value (original currency) | Actual Contract Value (USD) | Planned Completion Date (e.g. 21/08/2026)
📅 Blue columns = date fields ¦ Click any blue cell to see the date format guide ¦ Enter: 12-Aug-2026 (or: 2026-08-12)
ATFP-CTR-001 | Design and supervision services | 125000 | 2026-06-01 | 2026-06-08 | USD | 120000 | 120000 | 2026-12-12
ATFP-CTR-002 | Supply of laboratory equipment | 85000 | 2026-06-01 | 2026-07-15 | AUD | 128300 | 83500 | 2027-06-30